## Tabelle1
Deliverables | Name | Institution | Delivery date | Comments
D8.1 | Scratchpad modules engaging citizen scientists | HCMR | 12 | Done as a first version; In the description of the WP this has to be done by GBIF! (on the basis of our prototype)
D8.2 | Analytical and reporting tools | VIZZ | 24 | Still long time for it. We are progressing quite well with the first version for this released 2 weeks ago
D8.3 | Correction and annotation of GBIF observational data | GBIF | 36
Milestones for Year 1 (existing)
MS810 | Prototype scratchpads modules with ecological and conservation applications | HCMR | 6 | Done as a prototype, but needs implementation through WP 5 (Neil)
MS811 | Review of relevant field recording tools and applications | MFN Berlin | 6 | Done
MS812 | Identify rules for an intelligent algorithm to identify suspicious data records in GBIF data | GBIF | 12 | Done
MS813 | Define further milestones in the light of usage and feedback | HCMR | 12 | Done
MS814 | Prototype demonstration project with non-professional marine naturalists | HCMR | 12 | Done as a prototype
Milestones for Year 2 (existing)
MS815 | Report on existing processing services and analytical services | HCMR | 15 | To be done
MS816 | Prototype analytical tools and reporting tools implemented on the visualization tool | VIZZ | 18 | As said before we are still some months for the completition of this milestone, but we released 2 weeks ago the first version, just to be able to present it at TDWG. It can be seen at http://geocat.kew.org/
MS817 | APIs to integrate various data sources in support of analytical and reporting tools | HCMR | 18 | To be done
MS818 | Prototype scratchpad module with customisable visualizations of GBIF data | GBIF | 18 | To be done. This module should include annotation / correction facilities
MS819 | Customization of the reporting system for the IUCN Species Information System for endangered species | VIZZ | 22 | To be done | This is still months away. But we have an issue here. Our main contact at IUCN has just left his position and right now is not clear the agenda to make this happen. We were expecting to work on this at the beginning of 2012 but as I said plans have changed. We are having a meeting in Madrid with the IUCN Red List Program officer to draft a new agenda to make this happen.
Additional Milestones for Year 2 (proposed)
M8.XX | Scratchpads module for data recording (Citizen Science ) - Alpha version | HCMR | 18 | Install file of the whole system – needs about 1 month work by me or 2 months by Vangelis (part-time)
M8.XX | Data flow from GBIF annotation module to Biodiversity Data Journal (collaboration with WP6) in place | GBIF / PENSOFT | 22
M8.XX | Ecological and conservation applications implemented as a service (backend) (collaboration with WP 5) | HCMR / WP5 | 15 | Collaboration with WP6, little work from our side (the R bit, implementing the TaxDist algorithms etc and documentation of the code by Vavilis)
| Currently, the routines for calculating indices are written in C and can be executed on any machine which has a C compiler installed. | ? | 22 | This needs some thought and work and collaboration with WP2 and WP5
M8.XX | Integration of visualization applications with Scratchpads (collaboration with WP5) | VIZZ / WP5 | 18 | Depends on progress in WP 5