## Sheet1
| ID/Description | Due date | Lead partner | Document/URL
M4.10 | Define methods to use the Scratchpad service layer deliverable within the CDM store | 2011-05-31 | BGBM | http://vbrant.eu/sites/vbrant.eu/files/ViBRANT%20M410%20Specification%20...
M4.11 | Prototype of collaborative community interface | 2011-05-31 | JKI | http://vbrant.eu/sites/vbrant.eu/files/M4.11%E2%80%94Prototype%20of%20co...
M4.12 | Liaison and networking with ontology experts and existing ontology providers | 2011-07-31 | GBIF | http://vbrant.eu/sites/vbrant.eu/files/Smith-Submitted-v2Revised_ed_fina...
M4.13 | Release an API on the catalogue of resources | 2011-08-31 | JKI | http://vbrant.eu/sites/vbrant.eu/files/M4.13%20-%20Release%20an%20API%20...
D4.1 | Scratchpad common access point | 2011-11-30 | BGBM | http://vbrant.eu/sites/vbrant.eu/files/ViBRANT-D4.1.doc
M4.14 | Define further milestones in the light of usage and feedback | 2011-11-30 | UvA | WP4 milestones
M4.15 | Ontology Tools: migrate GBIF Vocabularies Service | 2011-12-31 | GBIF
M4.16 | Ontology Tools: scoping document on a KOS architecture | 2011-12-31 | GBIF
M4.17 | Extensions for DwC-A export functionality | 2012-02-28 | BGBM
M4.18 | Human Interface for CDM-ViBRANT Index | 2012-03-28 | BGBM
M4.19 | Canvassing glossary-oriented potential contributors | 2012-03-31 | JKI
M4.20 | Ontology Tools: new prototype (GBIF) Glossary of Terms registry | 2012-04-30 | GBIF
M4.21 | Ontology Tools: new prototype Biodiversity BioPortal | 2012-06-30 | GBIF
M4.22 | BiolFlor Data as semantic web | 2012-06-30 | JKI
D4.3 | Ongoing services enhancements | 2012-09-30 | BGBM
M4.23 | Scratchpad to DwC-A Mapping Module | 2012-09-30 | BGBM
M4.24 | Full text search CDM-ViBRANT Index | 2012-09-30 | BGBM
M4.25 | Pilot implementation of webservice at BGBM | 2012-09-30 | BGBM
M4.26 | Practical application milestone for media wiki | 2012-09-30 | BGBM
M4.27 | Audobon Core standard on Mediawiki | 2012-09-30 | JKI
M4.28 | Statistical output provided for CDM-ViBRANT Index query Interface | 2012-11-30 | BGBM
M4.29 | CDM SDD output optimised for Xper2 | 2012-11-30 | UPMC
M4.30 | Integrating the biowikifarm into ViBRANT authentication | 2012-11-30 | JKI
D4.2 | Ontology tools | 2012-12-31 | BGBM | Status report: http://vbrant.eu/sites/vbrant.eu/files/ViBRANT-D4.2.pdf
M4.31 | Webservice-Layer adapted for ViBRANT | 2013-01-31 | BGBM
M4.32 | Integrating a wiki-glossary into the scratchpad | 2013-01-31 | JKI
M4.33 | XML Transformations CDM export | 2013-04-30 | BGBM
M4.34 | Prototype for taxonomic generalisation | 2013-05-31 | UPMC
M4.35 | Filter functionality CDM export | 2013-05-31 | BGBM
M4.36 | XPer2-CDM-relation for taxonomic hierarchy specification | 2013-05-31 | UPMC
M4.37 | Xper2 and EDIT Platform publishing capability on Mediawiki | 2013-05-31 | UPMC